## Sheet1
Work reoport
Date | Task Started /Assigned | completion in Percentage | Issues if any
2017-09-28 | Formating Forms(33,32,36,39 | Task Completed | Form 20 not opening and Form 35,22 discussion with mam
2017-09-29 | Applied Ajax in CNCP | Task Completed | Ajax applied perfectly but alignment is disturbed.
2017-10-03 | Ajax + Alignment | Task Completed
2017-10-04 | Applied CSS on CWC and DCPU panel | Task Completed
2017-10-05 | Integration Of .jrxml of Form 36 and Corrected Code For Form 20 | Task Completed
2017-10-06 | Integration Of .jrxml of Form 32,33,39 | Task Completed
2017-10-09 | Integration Of .jrxml of Form 20 | Task Completed
2017-10-10 | Applying pagination on Form 22,35 | Task Completed
2017-10-11 | Worked on javascript for CDAC- Recruitment | 50%Completed
2017-10-12 | Worked on javascript for CDAC- Recruitment | 50%Completed
2017-10-13 | Integrating .jrxml of Form 22 | 40% Completed
2017-10-16 | Integrating .jrxml of Form 22 | 100% Completed
2017-10-17 | Integrating .jrxml of Form 35 | 50%Completed
2017-10-18 | Integrating .jrxml of Form 35 | 50%Completed
2017-10-23 | Integrating .jrxml of Form 35 | Task Completed
2017-10-27 | Regular Expression Validation on CDAC - Recruitment | Task started
2017-10-30 | Regular Expression Validation on CDAC - Recruitment
2017-10-31 | Regular Expression Validation on CDAC - Recruitment
2017-11-01 | Regular Expression Validation on CDAC - Recruitment
2017-11-02 | Regular Expression Validation on CDAC - Recruitment | Task Completed
03-11-2017 TO 22-11-2017
Changing whole CSS On Index page and Internal Pages
Designing Form 3,4,5,8,9,17 For CCL